## Defect Tracking log
DEFECT TRACKING LOG
Defect No. | Date Created | Defect Description | Steps to replicate issue | Expected | Priority | Status
DEF-1 | 2022-10-13 | Admin login page requesting for License key for software license verification | Issue occured once or twice when accessing the main admin login page | Login page should be accessible always | Medium | New
DEF-2 | 2022-10-20 | Number of bookings of each type shown only on main dashboard and not inside respective bookings and also not shown under revenue breakdown graph | Login using supplier credentials, click on any type of Booking like Pending, Confirmed, Cancelled, Paid or Refunded. The loaded window does not show count on top | Should display counts of each booking type just like on main dashboard | Medium | New
DEF-3 | 2022-10-20 | "Confirmed Bookings" incorrectly shown as "Confrimed Bookings" in admin and supplier dashboard | Login using admin or supplier credentials and check spelling | Should display "Confirmed Bookings" | Medium | New
DEF-4 | 2022-10-23 | Bookings link in Supplier dashboard showing error "Unable to load the requested file: admin/template.php" | Login using supplier credentials, click on Bookings | Should display all bookings | High | New
DEF-5 | 2022-10-26 | Clicking on Bookings from Admin dashbard gives "XSS Injection!" alert | Login to system using admin credentials and click on "Bookings" link | Bookings should be displayed | High | New
DEF-6 | 2022-10-27 | The amount field in "Add Funds" module shows amount as GBP irrespective of currency setting | Login to system using user credentials, click on Add Funds, check the currency displayed in Amount field | Should match the currency set on the top drop down on the website | High | New
DEF-7 | 2022-10-27 | Changing currency causes page reload and goes to Home page | Login to system using user credentials, click on Add Funds, change currency to any other | Should stay in the same window and amounts should now show in newly set currency | Low | New
DEF-8 | 2022-10-27 | Flights and Visa module unavailable in Supplier dashboard | Login to system using supplier credentials, and check left side panel of dashboard (Issue seems to be random and these modules are available at times) | These modules should always be available | High | New
DEF-9 | 2022-10-27 | Peformance issues noticed on running multiple consecutive tests, which gives API error and login page itself is not accessible | Accessing the website and performing some actions, logout and login again and repeat. Issue noticed after around 15 attempts back to back | Website should be stable irrespective of load | Medium | New
DEF-10 | 2022-10-30 | PHPTravels logo changes at times to an orange color "marco travel" logo | Issue is too random so uncertain about steps to replicate | Should always show only PHPtravels logo | Medium | New
DEF-11 | 2022-11-03 | Home page, phptravels.net and login page not accessible and shows Disk quota exceeded error | Issue occured once or twice when accessing the main page | Home and Login page should be accessible always | Medium | New

## Screenshots
Website not accessible | Modules missing in Supplier dashboard
Admin login issue | API Error on User/Agent login
Supplier login page unavailable
XSS Injection error |  | Confirmed booking spelling issue
Booking counts not displayed